## Existing
HC | Existing |  | NBL | Sathish feedback | Domain | Target |  |  |  | What IF
| ON | OFF |  |  |  | ON | OFF | Total |  | ON | OFF | Total
10 | 2 | 8 |  | 2 ON and 8 OFF | Enrollment | 1 | 9 | 10 |  | 1 | 9 | 10 | Daniel
10 | 2 | 8 |  | Optimizable to 2 ON and 8 OFF | Provider | 1 | 9 | 10 |  | 1 | 9 | 10 | Kalai
10 | 2 | 8 |  |  | Claims | 1 | 9 | 10 |  | 1 | 9 | 10
10 | 2 | 8 |  | have 2 buffers | Digital | 1 | 9 | 10 |  | 1 | 9 | 10
7 | 2 | 5 |  | 1 ON and 6 OFF | MyLife | 1 | 6 | 7 |  | 1 | 6 | 7
13 | 2 | 11 |  | Optimize Asc | EDI | 1 | 9 | 10 |  | 1 | 9 | 10 | jegadish
10 | 2 | 8 |  | Downsizing 3 offshore | Encounters | 1 | 9 | 10 |  | 1 | 9 | 10
4 | 1 | 3 |  | 2 modules - Optimize Offshore | SAP Finance | 1 | 4 | 5 |  | 1 | 4 | 5
3 | 1 | 2 |  | Optimize Asc | Clinical - Clin Auto | 1 | 3 | 4 |  | 1 | 3 | 4 | Bhavani
13 | 2 | 11 |  |  | Clinical - UM/CM | 1 | 9 | 10 |  | 1 | 9 | 10
[5 empty] | SharedServices |  |  | 0 |  |  |  | 0
4 | 1 | 3 |  | 1 Solid Automation 3 PM EST coverage | CrossProduct | 0 | 3 | 3 |  | 0 | 3 | 3
2 |  | 2 | 1 |  | AI Testing (QE for AI) | 0 | 2 | 2 |  | 0 | 2 | 2
4 | 1 | 3 | 3 | Recommended 1 ON | GenAI Team{Foundational Build) | 0 | 4 | 4 |  | 0 | 4 | 4
4 | 1 | 3 |  |  | TDM | 1 | 3 | 4 |  | 1 | 3 | 4 | Ranjeeth
2 | 1 | 1 |  |  | Platform Enablement TestingTools / Tools Admin | 0 | 1 | 1 |  | 0 | 1 | 1
TOTAL | 22 | 84 | 4 |  | Total | 11 | 89 | 100 |  | 11 | 89 | 100
106
[7 empty] | Target | 2026-10-15
| 11 | 89 | [5 empty] | 2026-11-01
[8 empty] | 2026-09-29 | Initiate ID creation
[8 empty] | 2026-09-30 | All Leads Selections
[8 empty] | 2026-10-02 | Care Source ID created
[8 empty] | 2026-10-09 | 50 % team to be onboarded
Megala
Md Naaeem
Danesh

## Hiring Tracker
First Name | Last Name | Location | Date of Joining | Domain | Level | Status | Location | Healthcare | Automation
Radhakrishnan | Kumaravel | Offshore | 2026-10-12 |  |  | Ascendion Pipeline |  |  |  | Healthcare SME
Bhargavi | Nichenamatla | Offshore | 2026-10-15 |  |  | Ascendion Pipeline |  |  |  | AI Lead
Renganathan | R | Offshore | 2026-10-15 |  |  | Ascendion Pipeline |  |  |  | AI Builders
Rahul | Macherla | Offshore | 2026-10-19 |  |  | Ascendion Pipeline |  |  |  | AI Builders
Abhishek | Gowda | Offshore | 2026-10-23 |  |  | Ascendion Pipeline |  |  |  | AI Builders
Ramya | Bhat | Offshore | 2026-10-28 |  |  | Ascendion Pipeline
Karthick | Ravichandran | Offshore | 2026-10-28 |  |  | Ascendion Pipeline
Jagan | S | Offshore | 2026-11-09 |  |  | Ascendion Pipeline
Mohammed | Irfan Khan J | Offshore | 2026-11-09 |  |  | Ascendion Pipeline
Harisha | P | Offshore | 2026-11-12 |  |  | Ascendion Pipeline
Geentanjali | S | Offshore | 2026-11-18 |  |  | Ascendion Pipeline
Meenakshi Sundaram | Murugappa | Offshore | 2026-11-23 |  |  | Ascendion Pipeline
Ashok Kumar | S | Offshore | 2026-11-26 |  |  | Ascendion Pipeline
Arunkumar | Charles | Onsite | 2026-07-01 | Plan Preview |  | Existing
Ganesha | SR | Offshore | 2026-07-01 | EDI |  | Existing
Sowjanya | Prathi | Offshore | 2026-07-01 | EDI |  | Existing
Jegadhish | Saravana Bavan | Onsite | 2026-04-01 | EDI |  | Existing
Ragamayi | Galla | Onsite | 2026-08-10 | EDI |  | Existing
Bhavani | Jaganathan Radhakrishnan | Onsite | 2026-04-01 | Clinical |  | Existing
Gopala Swamy | Kanda | Offshore | 2026-04-01 | EDI |  | Existing
Gomathi | Manogaran | Offshore | 2026-04-01 | Clinical |  | Existing
Vanitha | Thangathurai | Offshore | 2026-04-01 | EDI |  | Existing
Nithyanantham | V | Offshore | 2026-04-01 | Claims |  | Existing
Nalluri | Manohar | Offshore | 2026-07-01 | EDI |  | Existing
Vijaya | Vemula | Offshore | 2026-04-01 | EDI |  | Existing
Berin | Jeio K C | Offshore | 2026-04-01 | EDI |  | Existing
Dillikumar | R | Offshore | 2026-05-13 | Encounters |  | Existing
Manikandan | Balasubramani | Offshore | 2026-04-09 | Provider |  | Existing
Bhavya | BC | Offshore | 2026-05-13 | Encounters |  | Existing
Selva Ganesh | Murugadoss | Offshore | 2026-04-01 | Clinical |  | Existing
Alaguraja | Muthu | Offshore | 2026-04-01 | EDI |  | Existing
Vaitheeswaran | Sundararaj | Onsite | 2026-04-01 | Provider |  | Existing
Balaji | Selvaraj | Offshore | 2026-07-01 | Clinical |  | Existing
Abhishek | Gadwal R K | Onsite | 2026-05-04 | EDI |  | Existing
Chandrakanth | Pitchika | Offshore | 2026-04-01 | EDI |  | Existing
Ranjeet | Kasetty | Onsite | 2026-09-30 | TDM |  | Existing
Hrishikesh | Rode | Offshore | 2026-09-30 | TDM |  | Existing
Digital tester1 |  | Offshore | TBD | Digital |  | Identifying
Digital tester2 |  | Offshore | TBD | Digital |  | Identifying
Digital tester3 |  | Offshore | TBD | Digital |  | Identifying
Digital tester4 |  | Offshore | TBD | Digital |  | Identifying
Digital tester5 |  | Offshore | TBD | Digital |  | Identifying
Digital tester6 |  | Offshore | TBD | Digital |  | Identifying
Digital tester7 |  | Offshore | TBD | Digital |  | Identifying
Encounters Tester1 |  | Offshore | TBD | Encounters |  | Identifying
Encounters Tester2 |  | Offshore | TBD | Encounters |  | Identifying
Clinical Tester1 |  | Offshore | TBD | Clinical - UM/CM |  | Identifying
Clinical Tester2 |  | Offshore | TBD | Clinical - UM/CM |  | Identifying
SAP Tester 1 |  | Offshore | TBD | SAP |  | Identifying
Daniel | Franklin | Onsite | 2026-10-26 | Enrollment |  | Interview Selected | US
Maheshkumar | Reddy | Offshore | 2026-10-09 | CrossProduct |  | KT Ready | Hyderabad, Telangana | Enrollment/ Prior Auth | Selenium | Enrollment
Swathi | Kodumuru | Offshore | 2026-10-09 | Clinical |  | KT Ready | Hyderabad, Telangana | Care Management - Guiding Care/ EDI | Selenium / Playwright | Provider
Beula | Evangelin | Offshore | 2026-10-09 | Enrollment |  | KT Ready | Chennai, Tamil Nadu | Enrollment | Tosca | Claims
Rani | K | Offshore | 2026-10-09 | Encounters |  | KT Ready | Chennai, Tamil Nadu | Claims | Selenium / Tosca / Python | SAP Finance
Deepak | P | Offshore | 2026-10-09 | Claims |  | KT Ready | Bengaluru, Karnataka | Enrollment/ EDI | Playwright | Digital
Saurav | Patil | Offshore | 2026-10-09 | Claims |  | KT Ready | Pune, Maharashtra | Claims/ Benefits | Playwright / JavaScript / TypeScript | EDI
Manasa | Malisetti | Offshore | 2026-10-09 | Enrollment |  | KT Ready | Hyderabad, Telangana | Enrollment/ Encounter | Playwright | Encounters
Rajasulochana | Pandiyarajan | Offshore | 2026-10-09 | Provider |  | KT Ready | Chennai, Tamil Nadu |  | Selenium | Clinical - UM/CM
Alpana | Rakshit | Offshore | 2026-10-09 | Enrollment |  | KT Ready | Vadodara, Gujarat | Provider | Selenium | SharedServices-CrossProduct
Saranya | K | Offshore | 2026-10-09 | Claims |  | KT Ready | Chennai, Tamil Nadu | Claims / Benefits / Accumulators | Selenium | SharedServices-AI Testing
Sandeep | Dhamale | Offshore | 2026-10-09 | Digital |  | KT Ready | Mumbai, Maharashtra | Claims / EDI | Selenium/ Playwright/ Typesript | SharedServices-GenAI Team{Foundational Build)
Santhi | Mindi | Offshore | 2026-10-09 | Encounters |  | KT Ready | Bhubaneshwar, Odisha | Medicaid / Claims / EDI | Playwright / Selenium | SharedServices-TDM
Kiran | D | Offshore | 2026-10-09 | Digital |  | KT Ready | Hyderabad, Telangana | Claims | Playwright | Platform Enablement
Swetha | Singh | Offshore | 2026-10-09 | Digital |  | KT Ready | Bengaluru, Karnataka | Medicaid / Enrollment & Eligibility | Selenium / Playwright / Tosca | QE Architect
Kousalya | Sarathy | Offshore | 2026-10-09 | Claims |  | KT Ready | Chennai, Tamil Nadu | Enrollment & Eligibility | Playwright / JavaScript / TypeScript | QE SME
Prasada | Lakshmi | Onsite | 2026-09-28 | Digital |  | KT Ready
Vidyulutha | Mareddy | Onsite | 2026-09-28 | Clinical |  | KT Ready
Astha | Agrawal | Offshore | 2026-10-09 | Clinical |  | KT Ready | Ghaziabad, Uttar Pradesh | Claims | Playwright / TypeScript / Selenium | Healthcare SME
Aditya | Srivatsava | Offshore | 2026-10-09 | CrossProduct |  | KT Ready | Hyderabad, Telangana | EDI | AI | AI Lead
Rameswari | R | Offshore | 2026-10-09 | Encounters |  | KT Ready | Chennai, Tamil Nadu | Claims | Selenium / Python | AI Builders
Jakeer Hussain | N | Offshore | 2026-10-09 | TDM |  | KT Ready | Bengaluru, Karnataka
Anshi | Kumari | Offshore | 2026-10-09 | TDM |  | KT Ready | Bengaluru, Karnataka
Harshini | D | Offshore | 2026-10-09 | Clinical |  | KT Ready | Coimbatore, Tamil Nadu | Enrollment & Eligibility | Playwright with JavaScript
Parameshwaran | K | Offshore | 2026-10-09 | Clinical |  | KT Ready | Karur, Tamil Nadu | Enrollment & Claim | Playwright with Typescript
Mohanraj | Palanisamy | Offshore | 2026-10-09 | Claims |  | KT Ready | Coimbatore, Tamil Nadu | Claims | Selenium/ Playwright/ Java/ javascript
Mohammed | Ismail | Offshore | 2026-10-09 | Clinical |  | KT Ready | Coimbatore, Tamil Nadu | EDI | Playwright with JavaScript
Aravindh | R | Offshore | 2026-10-09 | Claims |  | KT Ready | Coimbatore, Tamil Nadu | Claims, EDI 837I, EDI 837P, Encounters | Selenium/ Java
Vasiharan | Suresh | Offshore | 2026-10-09 | Provider |  | KT Ready | Chennai, Tamil Nadu | EDI | Playwright with Java, Selenium with Java
Madhurima | Paturu | Offshore | 2026-10-09 | Provider |  | KT Ready | Bengaluru, Karnataka | Provider
Harshith | Talam | Offshore | 2026-10-09 | Digital |  | KT Ready | Eluru, Andhra Pradesh
Mehraj | Banglewale | Offshore | 2026-10-09 | Enrollment |  | KT Ready | Bengaluru, Karnataka
Srinu | Karnati | Offshore | 2026-10-15 | Platform Enablement |  | KT Ready
Meena | Penumatsa | Offshore | 2026-10-13 | Clinical |  | KT Ready
Ravi | Mareddy | Offshore | 2026-10-13 | Digital |  | KT Ready
Sharmilee | DeviPrasath | Offshore | 2026-10-13 | Encounters |  | KT Ready
Athira | Muganth | Offshore | 2026-10-13 | Claims |  | KT Ready
Udistara Varma | Vegeshna | Offshore | 2026-10-13 | Digital |  | KT Ready
Yamuna | Athivaram | Offshore | 2026-10-13 | Enrollment |  | KT Ready
Mayuri | Patode | Offshore | 2026-10-13 | Claims |  | KT Ready
Kalai Mani | Balamurugan | Onsite | 2026-10-12 | Provider |  | KT Ready
Amit | Verma | Offshore | 2026-10-15 | Platform Enablement |  | KT Ready
Rajeshwari | Shukmuniyappa | Offshore | 2026-10-14 | Encounters |  | Onboarding in Progress | Bangalore, Karnataka | Medicaid and medicare | Selenium | Clinical - Clin Auto
Tanmaya | Bisoi | Onsite | 2026-10-22 | Claims |  | Onboarding in Progress | US
Kiruthika | Guruswamy | Offshore | 2026-10-06 | CrossProduct |  | Onboarding in Progress | Chennai, Tamil Nadu
Annapoorani | Kalvarayan | Offshore | 2026-11-06 | Enrollment |  | Onboarding in Progress | Chennai, Tamil Nadu
Sharath | Purushotham | Onsite | 2026-10-15 | Digital |  | Onboarding in Progress | US
Ritika | Sethi | Onsite | 2026-10-26 | Encounters |  | Onboarding in Progress | US
Atamgbo | Ayuwu | Onsite | 2026-10-15 | Clinical |  | Onboarding in Progress | US
Kalyani | Kovuru | Onsite | 2026-10-19 | SAP |  | Onboarding in Progress | US
Suriya | Kathiravan | Offshore | 2026-10-12 | GenAI-Build |  | Onboarding in Progress
Desmond | Figaredo | Offshore | 2026-10-12 | GenAI-Build |  | Onboarding in Progress
Renuka | Balsubramanian | Offshore | 2026-10-12 | GenAI-Build |  | Onboarding in Progress
Grishma | Gangar | Offshore | 2026-10-12 | CXP |  | Onboarding in Progress

## HiringTracker-Infosys
First Name | Last Name | Location | Date of Joining | Domain | Level | Status | Location | Healthcare | Automation
Test | Test | Onsite | 2026-11-01 | CXP | Level 4 | KT Ready

## KT-Status
KT SUMMARY STATUS | [11 empty] | SIGN OFF
# | Application | RAG Status | KT Completion-Target | KT Completion - Actual | KT Start Date | Understanding Doc | Shadow | Reverse-KT | Reverse-Shadow | Steady State | Owner | Confidence level from QE Managers | Confidence level from EQE(vendor)
1 | Enrollment | Green | 33.33% | 8% | 2026-10-12 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 12 | 8.3333
2 | Provider |  | 33.33% | 8% | 2026-10-12 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 12 | 8.3333
3 | Claims |  | 20% | 0% | 2026-10-14 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 10 | 10
4 | Digital |  | 38.46% | 5% | 2026-10-09 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 13 | 7.6923
5 | MyLife |  | 38.46% | 5% | 2026-10-09 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 13 | 7.6923
6 | Encounters |  | 38.46% | 10% | 2026-10-09 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 13 | 7.6923
7 | SAP Finance | Red | 0% | 0% | 2026-10-19 | In Progress | 2026-10-28 | 2026-10-28 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 7 | 14.2857
8 | Clinical - UM/CM |  | 33.33% | 0% | 2026-10-12 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 12 | 8.3333
9 | CrossProduct |  | 33.33% | 0% | 2026-10-12 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 12 | 8.3333
10 | TDM |  | 38.46% | 10% | 2026-10-09 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 13 | 7.6923
11 | Platform Enablement TestingTools / Tools Admin |  | 33.33% | 0% | 2026-10-12 | In Progress | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 12 | 8.3333
12 | GenAI Build |  | 11.11% | 0% | 2026-10-15 | Not Started | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Ascendion |  |  | 9 | 11.1111
13 | Clinical - Clin Auto |  |  | - | - | - | - | - | - | - | Ascendion
14 | EDI |  |  | - | - | - | - | - | - | - | Ascendion
15 | AI Testing |  |  | - | - | - | - | - | - | - | Ascendion
15 | CXP |  | 11.11% | 0% | 2026-10-15 | Not Started | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 | Infosys |  |  | 9 | 11.1111
Formulas:
KT Completion-Target = IF([KT Start Date]>TODAY(),0%,NETWORKDAYS([KT Start Date],TODAY())*R3%)

## App & Wave Scope
APP & WAVE SCOPE
# | Application | Criticality | High Touch | Incumbent (Mentor anchor) | Ascendion Mentee lead | Onshore | Offshore | Single-person dep risk | Backup mentee | KT status
1 | Enrollment | [6 empty] | Med | TBD | In Progress
2 | Provider | [6 empty] | High | TBD | In Progress
3 | Claims | [6 empty] | High | TBD | In Progress
4 | Digital | [6 empty] | Med | TBD | In Progress
5 | MyLife | [6 empty] | Med | TBD | In Progress
6 | EDI | [6 empty] | Med | TBD | Not required
7 | Encounters | [6 empty] | TBD | TBD | In Progress
8 | SAP Finance | [6 empty] | TBD | TBD | Not started
9 | Clinical - Clin Auto | [6 empty] | TBD | TBD | Not required
10 | Clinical - UM/CM | [6 empty] | TBD | TBD | Not started (10/15)
11 | CrossProduct | [6 empty] | TBD | TBD | In Progress
12 | AI Testing | [6 empty] | TBD | TBD | Not required
13 | TDM | [6 empty] | TBD | TBD | In Progress
14 | Platform Enablement TestingTools / Tools Admin | [6 empty] | TBD | TBD | Not started
15 | GenAI Build | [6 empty] | TBD | TBD | Not started

## Transition - Progress by Domain
KT SUMMARY STATUS
# | Application | KT Start Date | Understanding Doc | Confidence level from QE Managers | Confidence level from Qes | KT Completion - Actual | KT Completion - Planned | Shadow | Reverse-KT | Reverse-Shadow | Steady State | Target vs Actuals | Transition Effectiveness | Steady-State Readiness | Takeover-ready | Rolloff gate | Target gate date
1 | Enrollment | 2026-10-12 | In Progress |  |  | 8 |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
2 | Provider | 2026-10-12 | In Progress |  |  | 8 |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
3 | Claims | 2026-10-14 | In Progress |  |  | 0% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
4 | Digital | 2026-10-09 | In Progress |  |  | 5% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
5 | MyLife | 2026-10-09 | In Progress |  |  | 5% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11
6 | EDI | - | - |  |  | - |  | - | - | - | - | - | - | - | - | - | -
7 | Encounters | 2026-10-09 | In Progress |  |  | 10% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
8 | SAP Finance | 2026-10-19 | In Progress |  |  | 0% |  | 2026-11-02 | 2026-10-28 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
9 | Clinical - Clin Auto | - | - |  |  | - |  | - | - | - | - | - | - | - | - | - | -
10 | Clinical - UM/CM | 2026-10-12 | In Progress |  |  | 0% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
11 | CrossProduct | 2026-10-12 | In Progress |  |  | 0% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
12 | AI Testing | - | - |  |  | - |  | - | - | - | - | - | - | - | - | - | -
13 | TDM | 2026-10-09 | In Progress |  |  | 10% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
14 | Platform Enablement TestingTools / Tools Admin | 2026-10-12 | In Progress |  |  | 0% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED
14 | GenAI Build | 2026-10-15 | Not Started |  |  | 0% |  | 2026-10-28 | 2026-10-19 | 2026-11-04 | 2026-11-11 |  | 0% | 0% | No | CLOSED

## Team Roster (hidden)
Domain | CareSource Manager | ON LEAD | DoJ | OFF LEAD | DoJ | KT Readiness | KT Plan
Enrollment | Christine | Daniel* | 2026-10-19 | Screening in Progress |  | Not Ready | In Progress
Provider | Christine | Kalai | 2026-10-12 | Rajasulochana | 2026-10-06 | Ready to Start | In Progress
Claims | Jennifer | Tanmay* |  | Nithy | 2026-10-06 | Ready to Start
SAP Finance | Jennifer | Kalyani* |  | Screening in Progress
Digital | Sundar | Sharath | 2026-10-31 | Sandheep Dhamle | 2026-10-06 | Starting Today | Finalized
MyLife | Sundar | Prasada lakshmi | 2026-10-07 | Sweta Singh | 2026-10-06 | Ready to Start | In Progress
EDI | Suganya | Jegadhish | 2026-10-06 | Alagu | 2026-10-06 | No KT needed | NA
Encounters | Suganya | Ritika Sethi* |  | Dilli | 2026-10-06 | Ready to Start | In Progress
Clinical - Clin Auto | Rommel | Bhavani | 2026-10-06 | Selva | 2026-10-06 | No KT needed | NA
Clinical - UM | Rommel | Ata |  | Swathi Kodumuru | 2026-10-06 | Ready to Start | In Progress
Clinical - CM | Rommel | Vidyulatha | 2026-10-07
SharedServices
CrossProduct | Rommel | NA |  | Mahesh Kumar | 2026-10-06 | Ready to Start | In Progress
AI Testing | Sathish | NA |  | Radhika | 2026-10-06 | Ready to Start | NA
GenAI Team{Foundational Build) | Sathish | NA |  | Screening in Progress
TDM | Sangeetha | Ranjeeth |  | Screening in Progress |  | Ready to Start | Finalized
Platform Enablement TestingTools / Tools Admin | Sangeetha | NA | 2026-10-06 | Amit Verma/Srini | 2026-10-12 | In Progress | Finalized
QE Architect | Sathish |  |  | Mohan R
QE SME | Sathish |  |  | Hariharan Krishnaraj
AI Advisory |  |  |  | Naveen Krishnamurthy
Healthcare SME |  |  |  | Illamathy En
AI Lead |  |  |  | Ansiya Thangal Kunju
AI Builders |  |  |  | Kruthika Ganesan / Sowmya Sridhar / Aaditya Nayar

## Interview Tracking-Summary (hidden)
Domain / Area | Onshore | Offshore | KT Readiness | Domain / Area | Onshore | Offshore
Provider | Kalai Mani (10/12) | Mani |  | Provider
Selected
Screened (30-Sep)
Enrollment | Daniel Franklin | Beula (Interview pending) |  | Enrollment
🟢 Selected
Interview Completed (29-Sep) ; Business Interview Completed on 30-Sep
Claims | Tanmaya | Nithi |  | Claims
🔴 Rejected
Interview Completed (28-Sep)
Encounter | Mohammed Naeem 🔴 Rejected | ⚪ |  | Encounter
Megala Kumar 🟡 Waitlist
Dhanesh 🔵 Profile Under Review
Clinical | Megala Kumar 🔴 Rejected | Swathi 🟢 Selected |  | Clinical
Vidhyulatha 🔴 Rejected
Cross Product | ⚪ | Maheshkumar Reddy 🟢 Selected |  | Cross Product
Digital | Danesh 🔴 Rejected | ⚪ |  | Digital
Prasada Lakshmi 🔵 Profile Shared for Review
PE | Shiva Prasad 🔴 Rejected | ⚪ |  | PE
TDM | Ranjeeth | Hrishikesh |  | TDM

## Interview Tracking (hidden)
CareSource Manager | Domain | Location | Candidate | Interview Date | Process | Decision
Suganya Balaji | Encounter QA Lead | Onshore | Megala Kumar | 2026-09-23 | Interview Completed | Waitlist
Jennifer Winders | Claims Lead | Onshore | Tanmaya | 2026-09-28 | Interview Completed | Rejected
Rommel Tatel | Clinical Lead | Onshore | Megala Kumar | 2026-09-28 | Interview Completed | Rejected
Rommel Tatel | Clinical Lead | Offshore | Swathi | 2026-09-28 | Interview Completed | Selected
Rommel Tatel | Cross Product Lead | Offshore | Maheshkumar Reddy | 2026-09-28 | Interview Completed | Selected
Suganya Balaji | Encounter QA Lead | Onshore | Mohammed Naeem | 2026-09-28 | Interview Completed | Rejected
Sundar | Digital | Onshore | Danesh | 2026-09-28 | Interview Completed | Rejected
Christine Huber | Enrollment QA Lead | Onshore | Daniel Franklin | 2026-09-29 | Interview Completed | Selected
Christine Huber | Provider QA Lead | Onshore | Kalai Mani | 2026-09-30 | Interview Completed | Selected
Rommel Tatel | Clinical Lead | Onshore | Vidyulatha | 2026-09-30 | Interview Completed | Rejected
Sangeetha | PE Lead | Onshore | Shiva Prasad | 2026-10-01 | Interview Completed | Rejected
Jennifer Winders | Claims Lead | Offshore | Manasa | 2026-10-02 | Interview Completed | Rejected
Jennifer Winders | Claims Lead | Offshore | Nithyanantham | 2026-10-02 | Interview Completed | Selected
Jennifer Winders | Claims Lead | Onshore | Archana | 2026-10-02 | Interview Completed | Rejected
Sundar | Digital | Onshore | Prasada Lakshmi | 2026-10-02 | Interview Completed | Selected
Sangeetha | PE Offshore Lead | Offshore | Renuka | 2026-10-05 | Interview Completed | Rejected
Sangeetha | PE Offshore Lead | Offshore | Amit Verma | 2026-10-05 | Interview Completed | Selected
Suganya Balaji | Encounters Lead | Onshore | Archana | 2026-10-05 | Interview Completed | Rejected
Suganya Balaji | Encounters Lead | Onshore | Vidyulatha | 2026-10-05 | Interview Completed | Rejected
Sundar | Digital | Offshore | Sweta Singh | 2026-10-05 | Interview Completed | Selected
Christine Huber | Enrollment QA Lead | Offshore | Beula | 2026-10-06 | Interview Completed | Rejected
Christine Huber | Provider QA Lead | Offshore | Raja Sulochana | 2026-10-06 | Interview Completed | Selected
Dinesh | Digital Sr Tester | Offshore | Harshith Talam | 2026-10-06 | Interview Completed | Selected
Dinesh | GenAI Engineer | Offshore | Suriya | 2026-10-06 | Interview Completed | Selected
Dinesh | GenAI Engineer | Offshore | Desmond | 2026-10-06 | Interview Completed | Selected
Dinesh | GenAI Engineer | Offshore | Renuka | 2026-10-06 | Interview Completed | Selected
Jennifer Winders | Claims SAP Lead | Onshore | Srinivas Parisa | 2026-10-06 | Interview Completed | Rejected
Sundar | Digital Lead | Offshore | Sandheep Dhamle | 2026-10-06 | Interview Completed | Selected
Sangeetha | PE Offshore Lead | Offshore | Srini | 2026-10-07 | Interview Completed | Selected
Suganya Balaji | Encounters Lead | Onshore | Vidyulatha | 2026-10-08 | Interview Completed | Selected
Christine Huber | Provider Sr Tester | Offshore | Madhurima Paturu | 2026-10-06 | Interview Completed | Selected
Jennifer Winders | Claims Sr Tester | Offshore | Saranya Koppuli |  | Interview Completed | Selected
Christine Huber | Enrollment Sr Tester | Offshore | Beula Evangelin | 2026-10-07 | Interview Completed | Selected

## Plan Summary (hidden)
EQE KT PLAN — CareSource
Highlevel
Stage | What happens |  | Exit evidence
Plan | Confirm mentor↔mentee, access, schedule, questionnaire issued |  | Signed per-app KT schedule + access confirmed
Knowledge Acquisition | Incumbent-led sessions across 14 knowledge areas; draft Understanding Doc |  | KA Coverage green; doc reviewed by CareSource
Shadow | Observe live testing/triage; incumbent still owns the work |  | Shadow log, drafted SOPs, automation backlog, KM-gap list
Reverse-KT / Reverse-Shadow | Ascendion does the work and teaches it back; incumbent scores |  | Transition Effectiveness ≥ 80%
Stabilization | Run day-to-day with on-call incumbent support only |  | Steady-State Readiness ≥ 80%
Steady-State | Full ownership; incumbent rolls off this app |  | Phase-gate sign-off + rolloff authorized
Phase calendar
Phase | Window (dates from original - needs change) | KT activity
0 — Pre-Planning |  | Access/BGV in flight, mentors named, questionnaire issued to Incumbant
1 — Knowledge Acquisition |  | KA across 14 areas; Understanding Docs drafted & reviewed
2 — Shadow / Reverse-Shadow |  | shadow then reverse-KT; Transition Effectiveness scored
3 — Stabilization |  | independent run; Steady-State Readiness scored; takeover & rolloff (gated)
4 — Steady-State |  | BAU

## KA Knowledge Areas
KNOWLEDGE ACQUISITION — 14 AREAS × APP
App | # | Knowledge area | Est. hrs | Mentor (Incumbant) | Mentee (Ascendion) | Planned start | Planned end | % complete | Status | Understanding doc? | Comments
▸ Claims
Claims | 1 | Application overview | 1 | TBD | TBD |  |  | 0 | Pending | No
Claims | 2 | Solution architecture | 1 | TBD | TBD |  |  | 0 | Pending | No
Claims | 3 | Functionality & features | 8 | TBD | TBD |  |  | 0 | Pending | No
Claims | 4 | Upstream/downstream integration & environments | 2.5 | TBD | TBD |  |  | 0 | Pending | No
Claims | 5 | Test strategy & master suite | 4 | TBD | TBD |  |  | 0 | Pending | No
Claims | 6 | Regression suite | 2 | TBD | TBD |  |  | 0 | Pending | No
Claims | 7 | Defect management (+ SLAs: S1 24h / S2 48h / S3 72h) | 2 | TBD | TBD |  |  | 0 | Pending | No
Claims | 8 | Test data management | 2 | TBD | TBD |  |  | 0 | Pending | No
Claims | 9 | Automation (framework, coverage, backlog) | 4 | TBD | TBD |  |  | 0 | Pending | No
Claims | 10 | Recent projects (last 12 months) | 4 | TBD | TBD |  |  | 0 | Pending | No
Claims | 11 | Inflight projects | 2 | TBD | TBD |  |  | 0 | Pending | No
Claims | 12 | Peak / open-enrollment-specific testing | 2 | TBD | TBD |  |  | 0 | Pending | No
Claims | 13 | Metrics & governance | 2 | TBD | TBD |  |  | 0 | Pending | No
Claims | 14 | Business stakeholders | 1 | TBD | TBD |  |  | 0 | Pending | No
▸ Encounter
Encounter | 1 | Application overview | 1 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 2 | Solution architecture | 1 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 3 | Functionality & features | 8 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 4 | Upstream/downstream integration & environments | 2.5 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 5 | Test strategy & master suite | 4 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 6 | Regression suite | 2 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 7 | Defect management (+ SLAs: S1 24h / S2 48h / S3 72h) | 2 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 8 | Test data management | 2 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 9 | Automation (framework, coverage, backlog) | 4 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 10 | Recent projects (last 12 months) | 4 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 11 | Inflight projects | 2 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 12 | Peak / open-enrollment-specific testing | 2 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 13 | Metrics & governance | 2 | TBD | TBD |  |  | 0 | Pending | No
Encounter | 14 | Business stakeholders | 1 | TBD | TBD |  |  | 0 | Pending | No
▸ Enrollment
Enrollment | 1 | Application overview | 1 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 2 | Solution architecture | 1 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 3 | Functionality & features | 8 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 4 | Upstream/downstream integration & environments | 2.5 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 5 | Test strategy & master suite | 4 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 6 | Regression suite | 2 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 7 | Defect management (+ SLAs: S1 24h / S2 48h / S3 72h) |  | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 8 | Test data management | 2 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 9 | Automation (framework, coverage, backlog) | 4 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 10 | Recent projects (last 12 months) | 4 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 11 | Inflight projects | 2 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 12 | Peak / open-enrollment-specific testing | 2 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 13 | Metrics & governance | 2 | TBD | TBD |  |  | 0 | Pending | No
Enrollment | 14 | Business stakeholders | 1 | TBD | TBD |  |  | 0 | Pending | No
▸ Provider
Provider | 1 | Application overview | 1 | TBD | TBD |  |  | 0 | Pending | No
Provider | 2 | Solution architecture | 1 | TBD | TBD |  |  | 0 | Pending | No
Provider | 3 | Functionality & features | 8 | TBD | TBD |  |  | 0 | Pending | No
Provider | 4 | Upstream/downstream integration & environments | 2.5 | TBD | TBD |  |  | 0 | Pending | No
Provider | 5 | Test strategy & master suite | 4 | TBD | TBD |  |  | 0 | Pending | No
Provider | 6 | Regression suite | 2 | TBD | TBD |  |  | 0 | Pending | No
Provider | 7 | Defect management (+ SLAs: S1 24h / S2 48h / S3 72h) | 2 | TBD | TBD |  |  | 0 | Pending | No
Provider | 8 | Test data management | 2 | TBD | TBD |  |  | 0 | Pending | No
Provider | 9 | Automation (framework, coverage, backlog) | 4 | TBD | TBD |  |  | 0 | Pending | No
Provider | 10 | Recent projects (last 12 months) | 4 | TBD | TBD |  |  | 0 | Pending | No
Provider | 11 | Inflight projects | 2 | TBD | TBD |  |  | 0 | Pending | No
Provider | 12 | Peak / open-enrollment-specific testing | 2 | TBD | TBD |  |  | 0 | Pending | No
Provider | 13 | Metrics & governance | 2 | TBD | TBD |  |  | 0 | Pending | No
Provider | 14 | Business stakeholders | 1 | TBD | TBD |  |  | 0 | Pending | No
▸ TDM
TDM | 1 | Application overview | 1 | TBD | TBD |  |  | 0 | Pending | No
TDM | 2 | Solution architecture | 1 | TBD | TBD |  |  | 0 | Pending | No
TDM | 3 | Functionality & features | 8 | TBD | TBD |  |  | 0 | Pending | No
TDM | 4 | Upstream/downstream integration & environments | 2.5 | TBD | TBD |  |  | 0 | Pending | No
TDM | 5 | Test strategy & master suite | 4 | TBD | TBD |  |  | 0 | Pending | No
TDM | 6 | Regression suite | 2 | TBD | TBD |  |  | 0 | Pending | No
TDM | 7 | Defect management (+ SLAs: S1 24h / S2 48h / S3 72h) | 2 | TBD | TBD |  |  | 0 | Pending | No
TDM | 8 | Test data management | 2 | TBD | TBD |  |  | 0 | Pending | No
TDM | 9 | Automation (framework, coverage, backlog) | 4 | TBD | TBD |  |  | 0 | Pending | No
TDM | 10 | Recent projects (last 12 months) | 4 | TBD | TBD |  |  | 0 | Pending | No
TDM | 11 | Inflight projects | 2 | TBD | TBD |  |  | 0 | Pending | No
TDM | 12 | Peak / open-enrollment-specific testing | 2 | TBD | TBD |  |  | 0 | Pending | No
TDM | 13 | Metrics & governance | 2 | TBD | TBD |  |  | 0 | Pending | No
TDM | 14 | Business stakeholders | 1 | TBD | TBD |  |  | 0 | Pending | No

## Discovery Questionnaire
INCUMBENT DISCOVERY QUESTIONNAIRE
# | Category | Question for incumbent | Response | Doc / link provided | Follow-up
1 | Release Management | Provide the release calendar by domain/app (waterfall vs agile) and sprint timelines.
2 | Release Management | Who coordinates releases; what docs are provided per release cycle?
3 | Release Management | Are testers involved in prod cutover, checkout, warranty testing?
4 | Release Management | How are lessons-learnt / retrospectives captured per release/sprint?
5 | Release Management | Formal change/scope-management process during test execution?
6 | Release Management | Process for urgent break-fixes / e-fixes / ad-hoc releases (timeline)?
7 | Environment & Data | Enterprise environment strategy / path-to-production doc?
8 | Environment & Data | Test environments per test type (SIT, E2E, UAT)?
9 | Environment & Data | Recurring environment/infra challenges (access, refresh, downtime)?
10 | Environment & Data | Data-refresh activities in lower environments and their timing?
11 | Environment & Data | Access request model per environment / by role?
12 | Environment & Data | Pre-prod / prod (read-only) access rules for on/offshore?
13 | Environment & Data | TDM responsibility — central team vs test team; data-masking/PHI rules?
14 | KPIs & Metrics | Full metric catalog across design, data, execution, defects (see master list).
15 | KPIs & Metrics | How is each metric captured — manual vs tool-automated (ALM/JIRA/Tableau)?
16 | KPIs & Metrics | Calculation/formula for each KPI.
17 | KPIs & Metrics | Reporting frequency, report copies, and stakeholder distribution.
18 | KPIs & Metrics | CI process when a KPI/metric misses target (RCA, tracking).
19 | Test Design & Exec | Testers' involvement in requirements/story grooming.
20 | Test Design & Exec | Uniform test-case template across apps? Share it.
21 | Test Design & Exec | Risk/issue/dependency (RAID) process and tooling.
22 | Test Design & Exec | Review & approval process for functional/system test cases.
23 | Test Design & Exec | Testers' role in design-doc review/sign-off.
24 | Test Design & Exec | Testers' role in unit-test coverage/results approval.
25 | Test Design & Exec | How are results captured and to whom communicated?
26 | Test Design & Exec | Requirements-traceability process for manual + automated cases.
27 | Test Design & Exec | Entry/exit criteria per test phase — share checklist.
28 | Estimation | Standard estimation template (waterfall + agile).
29 | Estimation | Are test estimates in the ALM/JIRA tool pre-sprint? Walk through.
30 | Defect Management | Standard defect tool + process walkthrough.
31 | Defect Management | Defect severity guidelines and resolution SLAs.
32 | Defect Management | Escalation procedure when defect SLAs are missed.
33 | Defect Management | How are cross-functional defects managed?
34 | Deliverables | Standard deliverable set per release — share templates.
35 | Deliverables | Do deliverables change by test nature (prod fix / regression / progression)?
36 | Deliverables | Sign-off process + RACI per deliverable.
37 | Deliverables | Central repository for all deliverables — location?

## KT Metrics & RAG
KT METRICS & RAG
# | Metric | Formula | What it tells us | Green | Amber | Red | Role | Planned | Actual | Health
1 | KA Session Coverage | KA sessions held / planned | Coverage of incumbent-led KA vs plan | 97–103% | 90–<97% or 103–110% | <90% or >110% | Leading | 100% | 0% | N/A
2 | SME Effort Utilization | Actual / planned mentor effort | Incumbent SME time actually spent vs committed | 90–110% | 70–<90% or 110–120% | <70% or >120% | Leading | 100% | 0% | N/A
3 | Transition Effectiveness | Weighted reverse-KT + stage-gate feedback score | Quality of knowledge absorbed (scored by incumbent+client) | ≥80% | 60–<80% | <60% | GATE | 100% | 0% | N/A
4 | KT Documentation Efficiency | Mandatory docs delivered / planned | Understanding docs, SOPs, runbooks received | 100% | 90–<100% | <90% | Leading | 100% | 0% | N/A
5 | KT Schedule Adherence | Actual / planned progress | On-track vs the dated KA/shadow plan | 95–105% | 85–<95% or 105–115% | <85% or >115% | Leading | 100% | 0% | N/A
6 | KV (Reverse-KT) Session Coverage | KV sessions held / planned | Coverage of teach-back/reverse-KT vs plan | 97–103% | 90–<97% or 103–110% | <90% or >110% | Leading | 100% | 0% | N/A
7 | Steady-State Readiness | Tasks done independently / total tasks | Ability to run BAU without mentor support | ≥80% | 70–<80% | <70% | GATE | 100% | 0% | N/A
8 | AI Agent readiness ?? |  | How ready are the agents from context?

## Phase Gates
PHASE GATES
Phase | Exit criterion (binary) | Met? (Y/N) | Evidence / metric | Sign-off — CareSource | Sign-off — Ascendion | Date
0 Pre-Planning | Named Incumbant mentor + confirmed access for each app | N
0 Pre-Planning | Discovery questionnaire issued to incumbent | N
1 KA | Understanding Doc drafted & reviewed by CareSource | N
1 KA | KA Session Coverage green (≥97%) | N
2 Shadow/Reverse | Shadow log + SOPs/runbooks + automation backlog delivered | N
2 Shadow/Reverse | Transition Effectiveness ≥ 80% | N
3 Stabilization | Steady-State Readiness ≥ 80% | N
3 Stabilization | Rolloff authorized — incumbent exits this app | N
4 Steady-State | BAU stable; Wave-2 KA started | N

## Access & Onboarding (hidden)
ACCESS & ONBOARDING FUNNEL
# | Name | Pod / App | Onshore/Offshore | BGV clear | CareSource ID | VM / laptop login | Tool access level | App groups | Ready for KT? | Comments
1 |  |  |  | No |  | No | L1 |  | No
2 |  |  |  | No |  | No | L1 |  | No
3 |  |  |  | No |  | No | L1 |  | No
4 |  |  |  | No |  | No | L1 |  | No
5 |  |  |  | No |  | No | L1 |  | No
6 |  |  |  | No |  | No | L1 |  | No
7 |  |  |  | No |  | No | L1 |  | No
8 |  |  |  | No |  | No | L1 |  | No
9 |  |  |  | No |  | No | L1 |  | No
10 |  |  |  | No |  | No | L1 |  | No
11 |  |  |  | No |  | No | L1 |  | No
12 |  |  |  | No |  | No | L1 |  | No
13 |  |  |  | No |  | No | L1 |  | No
14 |  |  |  | No |  | No | L1 |  | No
15 |  |  |  | No |  | No | L1 |  | No
16 |  |  |  | No |  | No | L1 |  | No
17 |  |  |  | No |  | No | L1 |  | No
18 |  |  |  | No |  | No | L1 |  | No
19 |  |  |  | No |  | No | L1 |  | No
20 |  |  |  | No |  | No | L1 |  | No

## Governance & Cadence
GOVERNANCE & CADENCE
Daily → weekly → phase-gate → monthly/quarterly · feeds Leadership/04_Weekly_Leadership_Governance_Pack.xlsx
Cadence | Ritual | Content | Owner | Audience | Distribution
Daily | Pod DSR | KA/shadow progress, blockers, no-show escalations | Pod lead | Ascendion + CareSource app owners | Email EOD
Weekly | KT status pack | Per-app: KA% · Reverse-KT% · Transition Effectiveness · Steady-State Readiness · rolloff-gate · risks | EQE Delivery Lead | CareSource steering | Deck, weekly
Per gate | Phase-gate review | Binary exit criteria sign-off per app | Delivery Lead + CareSource owner | Joint | Signed gate sheet
Monthly | Service review | Metrics trend, doc efficiency, Wave-2 readiness | Delivery Lead | CareSource + Ascendion mgmt | Deck
Quarterly | Steering committee | Strategic view, AAVA/AI adoption, next-quarter plan | Delivery Head | Sponsors | Deck

## KT RAID
KT RAID LOG
KT-specific risks · assumptions · issues · decisions
# | Type | App / scope | Description | Category | Owner | Raised | Due | Status | Mitigation / decision
1 | Risk | All | Incumbent (Incumbant) SME availability/goodwill during takeover | Risk | EQE Delivery Lead |  | Ongoing | Open | Named mentors + committed hours in writing; daily no-show escalation
2 | Risk | Enrollment/Provider/MyLife/Encounter | Peak/open-enrollment exposure | Risk | EQE Delivery Lead |  | Ongoing | Open | Peak carve-out + incumbent billable-on-standby through 1st peak intake

## POCs Client (hidden)
DELIVERY & Governance POCs
App1 | Client Reporting Manager | Incumbent Vendor Contact | Incumbent Vendor Lead | CareSource SME
Name
E-mail
App2 | Client Reporting Manager | Incumbent Vendor Contact | Incumbent Vendor Lead | CareSource SME
Name
E-mail
App3 | Client Reporting Manager | Incumbent Vendor Contact | Incumbent Vendor Lead | CareSource SME
Name
E-mail

## POCs Ascendion (hidden)
DELIVERY POCs & ESCALATION POINTS
Ascendion
All Towers | Primary | Service Operation Manager | Delivery Head
Name
Mobile
Work phone
CareSource E-mail
Ascendion E-mail

## PivotCandidate
Row Labels | Count of Status
Existing | 24
Onboarding in Progress | 10
Ascendion Pipeline | 13
KT Ready | 42
Login ID Issues | 3
Interview Selected | 1
Identifying | 2
Grand Total | 95

## Focus Areas (hidden)
| Focus | Status
1 | Candidate profiles by product area
2 | Interview and onboarding plan
3 | End-to-end transition plan
4 | Knowledge-transfer preparation
5 | Near-term staffing coverage
6 | Contract and SOW
7 | Live transition dashboard
ADO to track stories - Ascendion will manage
Product-area workload and staffing

## First KT Update (hidden)
Action Item | Status | Pending
Candidate profiles by product area | Candidate profiles shared with respective domain QE Managers by product area; currently under review. | SAP Finance, Tools Admin
Interview and onboarding plan | In discussion with domain QE Managers; scheduling in progress. Meeting invites to be sent by EOD Friday.
End-to-end transition plan | Transition plan shared in Excel format
Next step: translate into a live dashboard.
Live Transition Dashboard | Live dashboard to be built in Power BI (Ascendion environment) for on-demand visibility to CareSource management. WIP version available for preview tomorrow; target completion 9/28. A static HTML version will be shared first for feedback before finalizing.
Dependency on CareSource: support needed to host the source file in the CareSource environment
Knowledge-transfer preparation | a) Accelerated Bootcamp (pre-KT readiness) - Identified talent going through an accelerated bootcamp training as listed below
Orientation: Engagement overview, EQE goals, roles & responsibilities
Training: Healthcare domain + Playwright refresher sessions
Mentorship: SME assigned per domain for tools/process onboarding (ADO, qTest, Confluence, timesheets, access requests, AVD)
Knowledge and experience sharing sessions from current domain Leads
Periodic progress check-ins on KT readiness
b) AI-Assisted KT Enablement
Team mobilized to drive the KT process with Self Learning as focus
Named individuals identified and assigned to lead this effort, names shared with Individual Managers
c) AI-Assisted KT Assets
Knowledge agent vectorization + retrieval pipeline (Contextualization layer being built) - indexing GitHub repos and SharePoint documents into a searchable knowledge base
Chatbot solution being built on top of the indexed knowledge base for on-demand Q&A
Auto-generated documentation from the indexed content, in progress
Will require internal fine-tuning to adapt for CareSource’s domain specific context
M365 Copilot (Facilitator) to record and summarize KT sessions in Teams, feeding session outputs directly into the knowledge base
WIP demo available tomorrow
CareSource dependency: AAVA Contextualization service needs to be deployed in the CareSource environment (additional containers required); M365 Copilot license needed for the KT duration
Near-term staffing coverage | Key named individuals for Transition initiation across onshore and offshore shared
Onboarding and pre-KT for QEs will proceed in waves between Oct 1 and Nov 13, with week-on-week progress updates
Contract and SOW | Base SOW is being drafted by CareSource (Amanda); once received, Ascendion will review and finalize.